## Sheet1
Type	Description					Priority	Completion Time
Feature	Enable flash mode on/off; enable front and back camera					0	2019-01-30
Feature	Capture and retrieve the image					0	2019-02-06
Feature	Configure Realm					0	2019-02-07
Feature	Auto generate id for realm object					0	2019-02-07
Test	Add unit test to realm utilities					0	2019-02-07
Feature	Add timeline components					0	2019-02-08
Feature	Save photos to database and retrieve photos in timeline					0
Feature	Each image show a loading bar with white background at the very beginning of entering the timeline screen					5
Feature	Add PhotoDisplayScreen displayed when pressing the photo in timeline or after taking the photo
Feature	Add EditScreen to allow edit the photo
Feature
Feature
Feature
Feature
Feature	Collapse photos of a certain timeline when clicking the title of the certain timeline					5
Test	Add unit test to object utilities					5	2019-02-08
Refactor	Filter Query Builder					10